## Sheet1
Task ID | Task Name | Task Description | Start Date | End Date | Owner(s)/Resources | Dependency Type | Dependency ID
T1 | Backend Database & Routing Setup (SP-165) | Setup PostgreSQL, Express connection, and routing API | 2025-10-20 | 2025-10-22 | Shalini, Karan
T1.1 | Create PostgreSQL Schema (Part 1 – SP-134) | Base schema tables | 2025-10-20 | 2025-10-20 | Shalini
T1.2 | Create PostgreSQL Schema (Part 2 – SP-135) | Extended schema with relations | 2025-10-20 | 2025-10-20 | Karan | Finish-to-Start | T1.1
T1.3 | Connect Express to Database (SP-131) | Database connection and pooling | 2025-10-20 | 2025-10-20 | Karan | Finish-to-Start | T1.2
T1.4 | Implement Routing Functionality (Part 1 & 2) | Core and additional Express routes | 2025-10-21 | 2025-10-22 | Shalini | Finish-to-Start | T1.3
T1.5 | Postman API Testing (SP-133) | Test API endpoints via Postman | 2025-10-22 | 2025-10-23 | Shalini | Finish-to-Start | T1.4
T2 | Frontend UI Theme & Design (SP-137) | UI development and integration with backend | 2025-10-20 | 2025-10-23 | Shalini, Huda | Finish-to-Start | T1
T2.1 | Sign-Up Page (SP-145) | Frontend registration interface | 2025-10-20 | 2025-10-20 | Shalini
T2.2 | Login Page (SP-138) | Frontend login interface | 2025-10-20 | 2025-10-20 | Huda
T2.3 | User Profile Page (SP-139) | Profile management page | 2025-10-21 | 2025-10-22 | Shalini | Finish-to-Start | T1.3
T2.4 | Home Page (SP-140) | Home interface with maps | 2025-10-21 | 2025-10-22 | Huda | Finish-to-Start | T1.3
T2.5 | Suggested Routes Page (SP-141) | Route listing layout | 2025-10-22 | 2025-10-22 | Shalini | Finish-to-Start | T1.4
T2.6 | Hazard Reporting Page (SP-142) | Report hazard UI | 2025-10-22 | 2025-10-22 | Shalini | Finish-to-Start | T1.4
T2.7 | Find Buddy Page (SP-143) | Buddy matching feature | 2025-10-22 | 2025-10-23 | Shalini | Finish-to-Start | T2.3
T3 | UML & System Design Diagrams (SP-178) | Prepare UML, ER, and architecture diagrams | 2025-10-20 | 2025-10-22 | All | Finish-to-Start | T1, T2
T3.1 | Use Case Diagram | High-level user interaction representation | 2025-10-20 | 2025-10-21 | Priyanka | Finish-to-Start | T1
T3.2 | Class Diagram | System logical model | 2025-10-20 | 2025-10-22 | Shalini | Finish-to-Start | T1
T3.3 | Sequence Diagram | Component interaction flow | 2025-10-21 | 2025-10-22 | Hina | Finish-to-Start | T1, T2
T3.4 | Architecture Diagram | Deployment and system architecture layers | 2025-10-21 | 2025-10-22 | Karan | Finish-to-Start | T1
T3.5 | Database ER Diagram | Database relationships visualization | 2025-10-20 | 2025-10-21 | Shalini, Karan | Finish-to-Start | T1
T4 | Interim Report Writing (SP-73) | Compile report sections into final submission (Deadline 23 Oct 6 PM) | 2025-10-20 | 2025-10-23 | All | Finish-to-Start | T3
T4.1 | User Scenario (1.1) | Persona and motivation section | 2025-10-20 | 2025-10-21 | Hina, Shalini
T4.2 | Technical Problem (2.x) | System problem explanation with diagrams | 2025-10-21 | 2025-10-22 | Karan, Huda, Shalini | Finish-to-Start | T1, T3
T4.3 | Technical Solution (3.x) | Frontend, backend, and data resource explanation | 2025-10-21 | 2025-10-22 | Shalini, Karan, Huda, Hina | Finish-to-Start | T4.2
T4.4 | Evaluation (4.1) | Testing and success metrics | 2025-10-22 | 2025-10-23 | Hina, Shalini | Finish-to-Start | T4.3
T4.5 | Conclusion (5.1) | Project management and reflection | 2025-10-23 | 2025-10-23 | Shalini, Karan | Finish-to-Start | T4.4
T5 | Video Compilation & Individual Submissions (SP-149, SP-150) | Recordings & final compilation (Deadline 22 Oct 6 PM) | 2025-10-21 | 2025-10-22 | All | Finish-to-Start | T4
T6 | Interim Presentation (SP-163) | Slides, script, and rehearsal (Deadline 23 Oct 6 PM) | 2025-10-21 | 2025-10-23 | All | Finish-to-Start | T4
T6.1 | Slide Design | PowerPoint slide visuals | 2025-10-21 | 2025-10-22 | Huda | Finish-to-Start | T4.1
T6.2 | Demo Screenshots Integration | Integrate system visuals | 2025-10-22 | 2025-10-23 | Shalini, Karan | Finish-to-Start | T1, T2
T6.3 | Script & Rehearsal | Team coordination for presentation | 2025-10-23 | 2025-10-23 | All | Finish-to-Finish | T6.1, T6.2
T7 | Interim Demo (SP-164) | Live prototype demo in class (Friday) | 2025-10-24 | 2025-10-24 | All | Finish-to-Start | T6
T7.1 | Backend Demo | API functionality demo | 2025-10-24 | 2025-10-24 | Shalini, Karan | Finish-to-Start | T1
T7.2 | Frontend Demo | UI functionality demo | 2025-10-24 | 2025-10-24 | Shalini, Huda | Finish-to-Start | T2
T7.3 | Full System Walkthrough | Combined prototype demo & Q&A | 2025-10-24 | 2025-10-24 | All | Finish-to-Finish | T7.1, T7.2
T8 | Retrospective Document (SP-147) | Sprint 4 retrospective summary | 2025-10-25 | 2025-10-26 | Shalini | Finish-to-Start | T7
T9 | Reflective Diaries (SP-157) | Individual member reflections | 2025-10-25 | 2025-10-26 | All | Finish-to-Start | T7
T10 | GitHub & Jira Management (SP-156) | Continuous sprint tracking and updates | 2025-10-20 | 2025-10-26 | Shalini | Start-to-Start